## Copyright
Copyright Notice
The content in this file was created by Mynda Treacy from My Online Training Hub.
Individual users are permitted to recreate the examples for personal practice only.
Recreating the examples for training or demonstration to others is not permitted, unless written consent is granted by Mynda Treacy.
The workbook and any sheets within must be accompanied by the following copyright notice: My Online Training Hub ©.
This sheet must remain in any file that uses this data and or these techniques.
Any uses of this workbook and/or data must include the above attribution.
Social Channels

## Project Gantt
PROJECT TRACKER ¦ Website Redesign
TOTAL TASKS | 12 | COMPLETE | 2 | IN PROGRESS | 5 | NOT STARTED | 5 |  | Complete |  |  | In Progress |  |  | Remaining |  |  | Weekend |  |  | Today
TASK | PHASE | OWNER | START | DURATION | END | COMPLETED | PROGRESS | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27
Define project scope | Planning | Sarah | 2026-03-02 | 5 | 2026-03-06 | 5 | 100%
Stakeholder sign-off | Planning | Tom | 2026-03-04 | 3 | 2026-03-06 | 3 | 100%
User research & interviews | Planning | Sarah | 2026-03-06 | 6 | 2026-03-13 | 4 | 66.67%
Wireframes & mockups | Design | Priya | 2026-03-05 | 7 | 2026-03-13 | 3 | 42.86%
Brand & style guide | Design | Priya | 2026-03-10 | 10 | 2026-03-23 | 6 | 60%
Design review & feedback | Design | Tom | 2026-03-12 | 7 | 2026-03-20 | 0 | 0%
Backend development | Development | James | 2026-03-10 | 7 | 2026-03-18 | 4 | 57.14%
Frontend development | Development | Lisa | 2026-03-11 | 10 | 2026-03-24 | 2 | 20%
QA & testing | Development | James | 2026-03-17 | 5 | 2026-03-23 | 0 | 0%
Bug fixes & polish | Development | Lisa | 2026-03-19 | 5 | 2026-03-25 | 0 | 0%
Marketing prep | Launch | Tom | 2026-03-20 | 5 | 2026-03-26 | 0 | 0%
Go live | Launch | Sarah | 2026-03-27 | 1 | 2026-03-27 | 0 | 0%
read tutorial
watch tutorial

## More Resources
More Resources
Tutorials
Excel Functions | https://www.myonlinetraininghub.com/excel-functions
Charting Blog Posts | https://www.myonlinetraininghub.com/category/excel-charts
Excel Dashboard Blog Posts | https://www.myonlinetraininghub.com/category/excel-dashboard
Webinar Replays
Excel Dashboards & Power BI | https://www.myonlinetraininghub.com/excel-webinars
Courses
Advanced Excel | https://www.myonlinetraininghub.com/excel-expert-upgrade
Advanced Excel Formulas | https://www.myonlinetraininghub.com/advanced-excel-formulas-course
Power Query | https://www.myonlinetraininghub.com/excel-power-query-course
PivotTable Quick Start | https://www.myonlinetraininghub.com/excel-pivottable-course-quick-start
Xtreme PivotTables | https://www.myonlinetraininghub.com/excel-pivottable-course
Power Pivot | https://www.myonlinetraininghub.com/power-pivot-course
Excel Dashboards | https://www.myonlinetraininghub.com/excel-dashboard-course
Power BI | https://www.myonlinetraininghub.com/power-bi-course
PowerPoint | https://www.myonlinetraininghub.com/microsoft-powerpoint-course
Excel for Data Analysts Fast Track | https://www.myonlinetraininghub.com/excel-data-analyst
Excel for Decision Making Under Uncertainty | https://www.myonlinetraininghub.com/excel-for-decision-making-course
Excel for Finance Professionals | https://www.myonlinetraininghub.com/excel-for-finance-course
Excel Analysis ToolPak | https://www.myonlinetraininghub.com/excel-analysis-toolpak-course
Excel for Customer Service Professionals | https://www.myonlinetraininghub.com/excel-for-customer-service-professionals
Excel for Operations Management | https://www.myonlinetraininghub.com/excel-operations-management-course
Financial Modelling | https://www.myonlinetraininghub.com/financial-modelling-course
Copilot Essentials | https://www.myonlinetraininghub.com/copilot-essentials-course
PowerPoint | https://www.myonlinetraininghub.com/microsoft-powerpoint-course
Microsoft Word Masterclass | https://www.myonlinetraininghub.com/microsoft-word-course
Support
Excel Forum | https://www.myonlinetraininghub.com/excel-forum
Follow Us for more Tips & Tutorials