## M365 Gamba Prog 06.05.2025
Head Agreement No. | Project Schedule No. | Program | Contract No. | Contract Title | Contract Type | Total Contracted Amt (GST Incl) | Stakeholder Entity Name(s) | Stakeholder Type | Primary Stakeholder(s) Contact Name | Primary Stakeholder(s) Contract Role | Primary Stakeholder(s) Email Address | Primary Stakeholder Contact Nos. | Stakeholder(s) Status | Entity Address | Contract Start Date | Contract End Date | Actual Start Date | Actual End Date | Revised Contract End Date | Revised Contract Amount (GST Incl) | Variation Order No. | Variation Date | Variation Reference No. | Contract Status | NLC Project Code | Milestone Index Category | Milestone Index | Milestone Sub-Index | Milestone No. | Milestone | Milestone Contracted Year | Milestone Year Total (Incl) | Milestone Amt (Incl) | MS Year Quarter | Milestone Frequency | MS Payment Type | Milestone Delivery Start Date | Milestone Delivery End Date | Milestone Delivery Revised End Date | Milestone Status | Audit Status | Region | Program Coordinator | Project Officer(s) | Ranger Group | Modified On | Modified By | Created On | Created By | Version
|  |  |  | NT Gamba Eradication Project |  | 6455446.8 | DCCEEW |  | Dr Fiona Fraser |  |  | 0429 481 148 |  |  | 21/12/2023 | 30/06/2026 | 21/12/2023 | 31/07/2026 |  |  | 1 |  |  | Open |  | Grant Payments | 1.1 |  |  |  | Year 2023-2024 | 2997500 | [6 empty] | Enter Revised Date | Open |  | Contracts (CM) | #NAME? | #NAME? |  | 2026-08-06 |  | 2026-08-06
[28 empty] | 1.11 |  | 2023-24 Fin Yr Payment (Cont Exec dec 2023) | 2023-2024 |  | 797500 |  |  |  | 2023-01-12 | 31/12/2023 | Enter Revised Date | Open |  | West Arnhem (WA) | #NAME? | #NAME?
[28 empty] | 1.12 |  | Acceptance of Proj Plan, MERI, ToR | 2023-2024 |  | 1100000 |  |  |  | ######## | ######## | Enter Revised Date | Open |  | Contracts (CM) | #NAME? | #NAME?
[28 empty] | 1.13 |  | Acceptance of End of Control Season Report | 2023-2024 |  | 1100000 |  |  |  | 2024-01-04 | 30/04/2024 | Enter Revised Date | Open |  | Borroloola Barkly (BB) | #NAME? | #NAME?
[26 empty] | Grant Payments | 1.2 |  |  |  | Year 2024-2025 | 1595000 | [6 empty] | Enter Revised Date | Open |  | Contracts (CM) | #NAME? | #NAME?
[28 empty] | 1.2.1 |  | Acceptance of Annual Report |  |  | 495000 |  |  |  | 2024-01-08 | 31/08/2024 | Enter Revised Date | Open |  | Gamba Program (Gamba) | #NAME? | #NAME?
[28 empty] | 1.2.2 |  | Acceptance of End of Control Season Report |  |  | 1100000 |  |  | 31/05/2025 | 2025-01-04 | 30/05/2025 | 31/05/2025 | Open |  | Contracts (CM) | #NAME? | #NAME?
[26 empty] | Grant Payments | 1.3 |  |  |  | Year 2025-2026 | 1862946.8 | [6 empty] | Enter Revised Date | Open |  | Contracts (CM)
[28 empty] | 1.3.1 |  | Acceptance of Annual Report |  |  | 825000 |  |  | 31/09/2025 | 2025-01-08 | 30/09/2025 | 31/09/2025 | Open
[28 empty] | 1.3.2 |  | Acceptance of End of Control Season Report |  |  | 762946.8 |  |  | 31/05/2026 | 2026-01-04 | 30/05/2026 | 31/05/2026 | Open |  | Western Top End (WTE)
[28 empty] | 1.3.3 |  | Acceptance of Draft Final Report |  |  | 275000 |  |  |  | 2026-01-06 | 30/06/2026 | Enter Revised Date | Open
[28 empty] | 1.3.4 |  | Final Report Yr 2026-37 |  |  | $ - |  |  |  | 2026-01-07 | 31/07/2026 | Enter Revised Date | Open
[26 empty] | Progress Reports | 2.1 |  |  |  | Year 2023-2024 | [7 empty] | Enter Revised Date | Open
[28 empty] | 2.1.1 |  | Project Plan | [6 empty] | 2024-01-01 | 15/01/2024 | Enter Revised Date | Open
[28 empty] | 2.1.2 |  | MERI Plan | [6 empty] | 2024-01-02 | 14/02/2024 | Enter Revised Date | Open
[28 empty] | 2.1.3 |  | 2023-24 On-ground Activity | [6 empty] | 2024-01-02 | 14/02/2024 | Enter Revised Date | Open
[28 empty] | 2.1.4 |  | Est. Gamba Eradication Committee | [6 empty] | 2024-01-02 | 14/02/2024 | Enter Revised Date | Open
[28 empty] | 2.1.5 |  | End of Control Season 2023-24 Prog Report | [5 empty] | 31/05/2024 | 2024-01-04 | 30/04/2024 | 31/05/2024 | Open
[26 empty] | Progress Reports | 2.2 |  |  |  | Year 2024-2025 | [8 empty] | Open
[28 empty] | 2.2.1 |  | Annual Report 2023-24 | [5 empty] | 30/09/2024 | 2024-01-08 | 31/08/2024 | 30/09/2024 | Overdue
[28 empty] | 2.2.2 |  | End of Control Season 2024-25 Prog Report | [5 empty] | 31/05/2025 | 2025-01-04 | 30/04/2025 | 31/05/2025 | Open
[26 empty] | Progress Reports | 2.3 |  |  |  | Year 2025-2026 | [8 empty] | Open
[28 empty] | 2.3.1 |  | Annual Report 2024-25 | [5 empty] | 30/09/2025 | 2025-01-08 | 31/08/2025 | 30/09/2025 | Overdue
[28 empty] | 2.3.2 |  | End of Control Season 2025-26 Prog Report | [5 empty] | 31/05/2026 | 2026-01-04 | 30/04/2026 | 31/05/2026 | Open
[28 empty] | 2.3.3 |  | Draft Final Report | [6 empty] | 2026-01-06 | 15/06/2026 | Enter Revised Date | Open
[28 empty] | 2.3.4 |  | Final Report | [6 empty] | 2026-01-07 | 31/07/2026 | Enter Revised Date | Open
[26 empty] | Finance Reports |  | 2.3.5 |  | Audited Financial Statement | [6 empty] | 2026-01-07 | 31/07/2026 | 0 | Overdue
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open
[39 empty] | 0 | Open

## Current Date
2026-08-06

## Version
I
II
IV
V
VI
VII
VIII
IX
X
XI
XII
XIII
XIV

## Contract Type
Contract Type
Grant
Fee for Service
Specialist Consultancy
Program
Sub-contract

## Index Category
Category
General Contracts
Contract Administration
Contract Execution Payments
Procurement
Expenses
Closure
Interim Payments
Interim Invoices
Iterim Progress Reports
Finance
Budgets
RCTIs
Acquittals
Audited Financial Statement
Unaudited Financial Statement
Governance
Compliance
Risks
Consultancy
Planning
Surveys
Mapping
Control
Reviews
Fire
Meetings
CPIs
ACCUs
Training
Permits
Assessments
Land Use
Communications
Site Visits
CEO and Management
HCP

## Project Officer
Name | NLC Region
| West Arnhem | WA
| Victoria River District | VRD
| Borroloola Barkly | BB
| Western Top End | WTE
Gamba Program

## Modication Details
Modification
Dan Orian | CA
CFC Admin
Business Development
Anita Seden
Dorothy Ramsey
Bridie Velik Lord

## NLC Prog Coord
Region/Section | Designation | Program Coordinator
West Arnhem | WA | Peter Phillips
Victoria River District | VRD | Liza Schenkel
Borroloola Barkly | BB | Tim West
Western Top End | WTE | Timothy Burbur
Gamba Program | Gamba | Thomas Price
Contracts | Contracts | Dan Orian
LoC | LoC | Shane Bailey
Adaptive Management | AM | Xavier Espiau
Business Development | BD | Bridie Velik Lord

## Program
BU Program | Designation
Working on Country | WoC
Indigenous Ranger Program | IRP
Ranger Jobs Program | RJP
Arnhem Land Fire Abatement | ALFA
Savannah Fire Management | SFM
Learning on Country Childeren & Schooling Program | LoC
Saving Native Species Program (Gamba) | Gamba
Joint Management Parks | JMP
NTG Aboriginal Ranger Jobs Program | ARGP
Kakadu National Parks Program | KNP
Indigenous Protection Agency | IPA
Aboriginal Benefit Account | ABA
Northern Australia Quarantine Strategy | NAQS
Fee for Service | FFS
Capability Building Initiative | CBI

## CFC Region
Region | Program Coordinator | Project Officer(s)
West Arnhem (WA) | Peter Phillips | J Salt/A Gordon | #NAME? | #NAME?
Victoria River District (VRD) | Liza Schenkel | L Gordon
Borroloola Barkly (BB) | Tim West | M Pattison
Western Top End (WTE) | Tim BurBur | PV Wyk/SH Aziz
Gamba Program (Gamba) | Tom Price | D Alvarez/J Twycross
Contracts (CM) | Dan Orian | D Orian
Learning-on-Country (LoC) | Shane Bailey | K Ferdinand
Adaptive Management (MERI) | Xavier Espiau | X Espiau
Business Development (BD) | Bridie Velik Lord | BD Lord

## Entity Address
Address Type | Designation
Post Box Number | PO Box
Physical Address | Phy Add

## Audit
Audit Status | Designation
Audited | Aud
Unaudited | Uad
Not Required
udit

## Contact Contract Role
Contract Role
Contract Manager
Assistant Contract Manager
Project Officer
Coordinator
Advisor
Department Head
Director
Assistant Director
Project Manager
Assistant Project Manager

## Ranger Group
egion
All
Mardbalk
Yugul Mangi
Numburrindi
Njanma
Timber Creek
Wardaman
Wudikulpiyerr
Wagiman
Garawa
Waanyi Garawa
Elliott
Ganalanga Mindibirrina
Malak Malak
Garngi
Bulgul
Kenbi
NIL

## Stakeholder Status
Stakeholder Status
Primary
Secondary
Minor
Alternative

## MS Payment Type
MS Payment Type
On Contract Execution
Interim
Final
RCTI

## Stakeholder Name
Stakeholder | Designation
National Indigenous Australian Agency | NIAA
Indigenous Land and Sea Corporation | ILSC
Commonwealth of Australia | CoA
National Australian Quarantine Service | NAQS
Northern Territory Government | NTG
Department of Climate Change, Energy, Environment and Water | DCCEEW
Department of Agriculture, Fisheries and Forestry | DAFF
Arnhem Land Fire Abatement NT Ltd | ALFA NT Ltd
Commonwealth Scientific and Industry Research Organization | CSIRO
National Australian Indigenous Land and Sea Management | NAILSMA
Department of Finance Canberra | DoF
Department of Infrastructure, Planning and Land | DIPL
Director of National Parks | DNP

## Stakeholder Type
Stakeholder Type
Internal
External

## Reports
Reports
Performance
Finance
Contract Administration
Consultancy
Fee for Service
Cost Recovery
Acquittals
Senate