## New data
|  |  | On Track | "Maybe" On Track | Not Going Ahead | Date Changed | Entered into the Gantt | Relevant Columns for CCC
Project | Status | Project Manager | Implementation Type | PM Meeting 2 weeks prior to system arrival on site | L400 Description | L400 Arrival on Site | CSE Site Status Discusion with PM mid week of Mech. Install | L490 Mech. Install Start
PRJ0407621: Bella Vista ¦ Norwest Priv Hosp ¦ Cios Flow ¦ 0056044132 | 10 | Angela Pierides | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-05 |  | 2025-05-06
PRJ0403431: Camperdown ¦ Royal Prince Alfred Hospital ¦ Upgrade Sensis ¦ 0056039979 | 10 | Jason Fung | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-09 |  | 2025-05-10
PRJ0397205: Coffs Harbour ¦ Coffs Harbour Base Hospital ¦ YSIO X.pree ¦ 0056038275 | 10 | Leon Rochead | Replacement |  | SOMATOM go.Top | 2025-05-12 |  | 2025-05-13
PRJ0393961: Kogarah ¦ St George Hospital ¦ ARTIS pheno (VE2X) ¦ 0056037266 | 10 | Katrina Reidpath | Replacement |  | Symbia Pro.specta Q3 System | 2025-05-08 |  | 2025-05-12
PRJ0337181: Kogarah ¦ Lumus Imaging St George Priv Hosp ¦ Multitom Rax ¦ 0056037358 | 20 | Katrina Reidpath | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-26 |  | 2025-05-26
PRJ0392280: Leichhardt ¦ I-MED Vet/Medipaws ¦ Cios Select VA21 II ¦ 0056036602 | 20 | Angela Pierides | New Install |  | 0 | 2025-05-30 |  | 2025-06-03
PRJ0410098: Coffs Harbour ¦ Coffs Harbour Base Hospital ¦ Upgrade PURE Artis zee / Q systems ¦ 0056045633 | 10 | Isabella Corsello | New Install |  | 0 | 2025-06-04 |  | 2025-06-04
PRJ0393532: Westmead ¦ The Childrens Hospital at Westmead ¦ ARTIS icono biplane Pro ¦ 0056037118 | 20 | Leon Rochead | New Install |  | 0 | 2025-06-04 |  | 2025-06-09
PRJ0407432: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044021 | 10 | Angela Pierides | New Install |  | ACUSON Freestyle Mainframe | 2025-07-14 |  | 2025-07-14
PRJ0407433: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044023 | 10 | Angela Pierides | New Install |  | 0 | 2025-07-14 |  | 2025-07-14
PRJ0407434: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044018 | 10 | Angela Pierides | New Install |  | 0 | 2025-07-14 |  | 2025-07-14
PRJ0396723: Randwick ¦ Prince of Wales Public Hospital ¦ ARTIS pheno (VE2X) ¦ 0056038133 | 20 | Leon Rochead | New Install |  | Symbia Pro.specta Q3 System | 2025-07-21 |  | 2025-07-21
PRJ0403095: Deakin ¦ Atlas Medical Imaging ¦ MULTIX Impact ¦ 0056039725 | 30 | Jim Forster | New Install |  | Symbia Pro.specta Q3 System | 2025-08-19 |  | 2025-08-25
PRJ0400728: Kogarah ¦ St George Hospital ¦ Sensis ¦ 0056039332 | 30 | Sinead Manning | New Install |  | SOMATOM go.All | 2025-09-01 |  | 2025-09-01
PRJ0407429: North Tamworth ¦ Tamworth Hospital ¦ Upgrade Sensis ¦ 0056044020 | 10 | Jason Fung | Replacement |  | SOMATOM go.Top | 2025-08-28 |  | 2025-08-28
PRJ0407440: North Tamworth ¦ Tamworth Hospital ¦ ARTIS icono floor ¦ 0056044065 | 10 | Jason Fung | Replacement |  | 0 | 2025-08-28 |  | 2025-08-28
PRJ0403079: Deakin ¦ Atlas Medical Imaging ¦ MAMMOMAT B.brilliant ¦ 0056039726 | 30 | Jim Forster | New Install |  | SOMATOM go.Top | 2025-08-19 |  | 2025-09-01
PRJ0371884: Nowra ¦ Illawarra Shoalhaven LHD ¦ YSIO X.pree ¦ 0056030499 | 30 | Katrina Reidpath | New Install |  | 0 | 2025-10-08 |  | 2025-10-08
PRJ0371885: Nowra ¦ Illawarra Shoalhaven LHD ¦ YSIO X.pree ¦ 0056030500 | 30 | Katrina Reidpath | New Install |  | SOMATOM go.Open Pro | 2025-10-08 |  | 2025-10-08
PRJ0371558: Nowra ¦ Illawarra Shoalhaven LHD ¦ Multitom Rax ¦ 0056030306 | 30 | Katrina Reidpath | New Install |  | Biograph Trinion EP | 2025-10-08 |  | 2025-10-08
PRJ0386864: North Ryde ¦ ADM Sydney Pty Limited ¦ Cios Select VA21 FD ¦ 0056034724 | 30 | Angela Pierides | New Install |  | SOMATOM go.All | 2025-11-03 |  | 2025-11-03
PRJ0389544: North Ryde ¦ ADM Sydney Pty Limited ¦ MULTIX Impact E ¦ 0056035596 | 30 | Angela Pierides | New Install |  | Biograph Trinion EP | 2025-11-03 |  | 2025-11-03
PRJ0405139: Camperdown ¦ Royal Prince Alfred Hospital ¦ ARTIS pheno (VE2X) ¦ 0056043183 | 30 | Jason Fung | Replacement |  | NAEOTOM Alpha.Pro | 2025-11-17 |  | 2025-11-17
PRJ0388978: Kingswood ¦ Nepean Hospital ¦ ARTIS icono ceiling ¦ 0056035282 | 30 | Hans Einoder Roca | New Install |  | Symbia Intevo 2 System | 2026-04-15 |  | 2026-04-15
PRJ0388046: Bass Hill ¦ Bass Hill Diagnostics ¦ MAMMOMAT Revelation ¦ 0056034978 | 30 | Jason Fung | New Install |  | 0 | 2026-05-11 |  | 2026-05-11
PRJ0405160: Macquarie Park ¦ Siemens Healthcare ¦ MOBILETT Elara Max ¦ 4532319400 | 10 | Kia Looi Low | Order to stock from demo |  | 0 | 2025-07-11
PRJ0404392: null ¦ Siemens Healthcare ¦ Cios Flow ¦ 4532301964 | 10 | Kia Looi Low | Order to stock from demo |  | ACUSON Freestyle Mainframe | 2025-04-14
PRJ0404415: ​​​​​​​Macquarie Park ¦ Siemens Healthcare ¦ Cios Flow ¦ 4532302071 | 10 | Kia Looi Low | Order to stock from demo |  | Biograph Trinion EP2 | 2025-04-14

## previous week
|  |  | On Track | "Maybe" On Track | Not Going Ahead | Date Changed | Entered into the Gantt | Relevant Columns for CCC
Project | Status | Project Manager | Implementation Type | PM Meeting 2 weeks prior to system arrival on site | L400 Description | L400 Arrival on Site | CSE Site Status Discusion with PM mid week of Mech. Install | L490 Mech. Install Start
PRJ0407621: Bella Vista ¦ Norwest Priv Hosp ¦ Cios Flow ¦ 0056044132 | 10 | Angela Pierides | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-05 |  | 2025-05-06
PRJ0403431: Camperdown ¦ Royal Prince Alfred Hospital ¦ Upgrade Sensis ¦ 0056039979 | 10 | Jason Fung | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-09 |  | 2025-05-10
PRJ0397205: Coffs Harbour ¦ Coffs Harbour Base Hospital ¦ YSIO X.pree ¦ 0056038275 | 10 | Leon Rochead | Replacement |  | SOMATOM go.Top | 2025-05-12 |  | 2025-05-13
PRJ0393961: Kogarah ¦ St George Hospital ¦ ARTIS pheno (VE2X) ¦ 0056037266 | 10 | Katrina Reidpath | Replacement |  | Symbia Pro.specta Q3 System | 2025-05-08 |  | 2025-05-12
PRJ0337181: Kogarah ¦ Lumus Imaging St George Priv Hosp ¦ Multitom Rax ¦ 0056037358 | 20 | Katrina Reidpath | Replacement |  | SEQUOIA SELECT EDITION | 2025-05-26 |  | 2025-05-26
PRJ0392280: Leichhardt ¦ I-MED Vet/Medipaws ¦ Cios Select VA21 II ¦ 0056036602 | 20 | Angela Pierides | New Install |  |  | 2025-05-30 |  | 2025-06-03
PRJ0410098: Coffs Harbour ¦ Coffs Harbour Base Hospital ¦ Upgrade PURE Artis zee / Q systems ¦ 0056045633 | 10 | Isabella Corsello | New Install |  |  | 2025-06-04 |  | 2025-06-04
PRJ0393532: Westmead ¦ The Childrens Hospital at Westmead ¦ ARTIS icono biplane Pro ¦ 0056037118 | 20 | Leon Rochead | New Install |  |  | 2025-06-04 |  | 2025-06-09
PRJ0407432: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044021 | 10 | Angela Pierides | New Install |  | ACUSON Freestyle Mainframe | 2025-07-14 |  | 2025-07-14
PRJ0407433: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044023 | 10 | Angela Pierides | New Install |  |  | 2025-07-14 |  | 2025-07-14
PRJ0407434: Camperdown ¦ Royal Prince Alfred Hospital ¦ Cios Flow ¦ 0056044018 | 10 | Angela Pierides | New Install |  |  | 2025-07-14 |  | 2025-07-14
PRJ0396723: Randwick ¦ Prince of Wales Public Hospital ¦ ARTIS pheno (VE2X) ¦ 0056038133 | 20 | Leon Rochead | New Install |  | Symbia Pro.specta Q3 System | 2025-07-21 |  | 2025-07-21
PRJ0403095: Deakin ¦ Atlas Medical Imaging ¦ MULTIX Impact ¦ 0056039725 | 30 | Jim Forster | New Install |  | Symbia Pro.specta Q3 System | 2025-08-19 |  | 2025-08-25
PRJ0400728: Kogarah ¦ St George Hospital ¦ Sensis ¦ 0056039332 | 30 | Sinead Manning | New Install |  | SOMATOM go.All | 2025-09-01 |  | 2025-09-01
PRJ0407429: North Tamworth ¦ Tamworth Hospital ¦ Upgrade Sensis ¦ 0056044020 | 10 | Jason Fung | Replacement |  | SOMATOM go.Top | 2025-08-28 |  | 2025-08-28
PRJ0407440: North Tamworth ¦ Tamworth Hospital ¦ ARTIS icono floor ¦ 0056044065 | 10 | Jason Fung | Replacement |  |  | 2025-08-28 |  | 2025-08-28
PRJ0403079: Deakin ¦ Atlas Medical Imaging ¦ MAMMOMAT B.brilliant ¦ 0056039726 | 30 | Jim Forster | New Install |  | SOMATOM go.Top | 2025-08-19 |  | 2025-09-01
PRJ0371884: Nowra ¦ Illawarra Shoalhaven LHD ¦ YSIO X.pree ¦ 0056030499 | 30 | Katrina Reidpath | New Install |  |  | 2025-10-08 |  | 2025-10-08
PRJ0371885: Nowra ¦ Illawarra Shoalhaven LHD ¦ YSIO X.pree ¦ 0056030500 | 30 | Katrina Reidpath | New Install |  | SOMATOM go.Open Pro | 2025-10-08 |  | 2025-10-08
PRJ0371558: Nowra ¦ Illawarra Shoalhaven LHD ¦ Multitom Rax ¦ 0056030306 | 30 | Katrina Reidpath | New Install |  | Biograph Trinion EP | 2025-10-08 |  | 2025-10-08
PRJ0386864: North Ryde ¦ ADM Sydney Pty Limited ¦ Cios Select VA21 FD ¦ 0056034724 | 30 | Angela Pierides | New Install |  | SOMATOM go.All | 2025-11-03 |  | 2025-11-03
PRJ0389544: North Ryde ¦ ADM Sydney Pty Limited ¦ MULTIX Impact E ¦ 0056035596 | 30 | Angela Pierides | New Install |  | Biograph Trinion EP | 2025-11-03 |  | 2025-11-03
PRJ0405139: Camperdown ¦ Royal Prince Alfred Hospital ¦ ARTIS pheno (VE2X) ¦ 0056043183 | 30 | Jason Fung | Replacement |  | NAEOTOM Alpha.Pro | 2025-11-17 |  | 2025-11-17
PRJ0388978: Kingswood ¦ Nepean Hospital ¦ ARTIS icono ceiling ¦ 0056035282 | 30 | Hans Einoder Roca | New Install |  | Symbia Intevo 2 System | 2026-04-15 |  | 2026-04-15
PRJ0388046: Bass Hill ¦ Bass Hill Diagnostics ¦ MAMMOMAT Revelation ¦ 0056034978 | 30 | Jason Fung | New Install |  |  | 2026-05-11 |  | 2026-05-11
PRJ0405160: Macquarie Park ¦ Siemens Healthcare ¦ MOBILETT Elara Max ¦ 4532319400 | 10 | Kia Looi Low | Order to stock from demo |  |  | 2025-07-11
PRJ0404392: null ¦ Siemens Healthcare ¦ Cios Flow ¦ 4532301964 | 10 | Kia Looi Low | Order to stock from demo |  | ACUSON Freestyle Mainframe | 2025-04-14
PRJ0404415: ​​​​​​​Macquarie Park ¦ Siemens Healthcare ¦ Cios Flow ¦ 4532302071 | 10 | Kia Looi Low | Order to stock from demo |  | Biograph Trinion EP2 | 2025-04-14
SOMATOM Force
NAEOTOM Alpha.Pro
SOMATOM go.Sim
SOMATOM Force
SOMATOM go.All